## Sprint 2
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As a customer, I want to be able to record my age, weight, height, and gender to see a suggestion for daily caloric intake. | Collect user info & give a suggested daily calorie intake based on this info | 2 | F : T | 1 |  | Vincent King
As someone trying to gain weight, I want to be able to set a weight goal to receive a suggested daily caloric intake. |  | 2 | F : T | 1 |  | Raven Goodell
As someone who is happy with their current weight, I want a built-in calorie calculator so I know how many calories I should consume to maintain my current weight. |  | 2 | F : T | 1 |  | Chris Vogel
As someone who struggles with an eating disorder, I do not want to be encouraged to lose weight. |  | 2 | NF : T | 2 |  | Travis Tovey
Garrett Caruso

## Sprint 3
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As someone trying to get in shape, I want to be able to calculate what macronutrients I need to consume to reach my fitness goals. |  | 3 | F : T | 2 |  | Vincent King
As someone trying to gain muscle, I want to receive suggestions on macronutrient intake based on my current intake to adjust my intake accordingly. |  | 3 | F : T | 2 |  | Raven Goodell
As someone trying to lose weight, I want to set custom weight loss goals so that the app will be more personalized to my needs. |  | 3 | F : T | 2 |  | Chris Vogel
As someone trying to lose weight, I want to be able to track my progress towards my weight loss goal so that I can see how I am progressing. |  | 3 | F : T | 2 |  | Travis Tovey
Garrett Caruso

## Sprint 4
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As a visual learner, I want a feature that will show me how many calories I've consumed each day in the form of a graph so that I can visually track my progress. |  | 4 | F : T | 2 |  | Vincent King
As someone trying to eat healthier, I want to be able to record my sugar and sodium intake to track how close I am to my maximum recommended daily intake. |  | 4 | F : T | 2 |  | Raven Goodell
Chris Vogel
Travis Tovey
Garrett Caruso

## Sprint 5
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As an app user, I want to be able to scan the barcode of packaged foods so that I can track my daily calorie intake more conveniently and accurately. |  | 5 | F : T | 4 |  | Vincent King
As a user, I want to have calorie and macronutrient estimates for foods that do not have a nutrition label (e.g. fruits and vegetables) to help keep track of my daily intake. |  | 5 | F : T | 1 |  | Raven Goodell
As an app user, I want a simple user interface to allow for easy navigation. |  | 5 | NF : T | 2 |  | Chris Vogel
Travis Tovey
Garrett Caruso

## Sprint 6
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As an app user, I want to be able to input calories by searching for food so that I can log foods that do not have a barcode. |  | 6 | F : T | 1 |  | Vincent King
As someone with visual problems, I want to be able to adjust font size to make the app more accessible. |  | 6 | F : T | 1 |  | Raven Goodell
As a colorblind person, I want the interface of the app to be colorblind friendly to make the app more accessible. |  | 6 | F : T | 2 |  | Chris Vogel
Travis Tovey
Garrett Caruso

## Sprint 7
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As a customer, I want to be able to set custom notifications and reminders so that I don't forget to log my data. |  | 7 | F : T | 2 |  | Vincent King
As an app user, I want to be able to select my preferred way of measuring food so that the daily log of calories I've consumed will be more accurate. |  | 7 | F : T | 1 |  | Raven Goodell
As someone who weighs food with a food scale, I want to input my foods in grams or ounces instead of suggested serving sizes. |  | 7 | F : T | 2 |  | Chris Vogel
As an app user, I want the app's notifications to be positive and encouraging so that I will be more motivated to use the app to track my calorie intake. |  | 7 | NF : T | 1 |  | Travis Tovey
Garrett Caruso

## Sprint 8
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As someone just starting their weight loss journey, I want an optional tutorial to show me how the app works so that I do not feel intimidated. |  | 8 | F : T | 2 |  | Vincent King
As an app user, I want the app to have a dark mode so that it will not strain my eyes as much. |  | 8 | F : T | 1 |  | Raven Goodell
As an app user, I want a feature that will allow me to track how much water I drink in a day so that I can make sure I am getting a proper amount of hydration. |  | 8 | F : T | 1 |  | Chris Vogel
As an app user, I want to be able to change the color palette of the app's interface so that it will be more personalize and nicer to look at. |  | 8 | F : T | 2 |  | Travis Tovey
Garrett Caruso

## Sprint 9
User Story | Sprint Goal | Sprint # | Story Type | Story Points | Story Points Completed | Team Members | % of Contribution to Story
As an avid gym-goer, I want a feature that will allow me to log my workouts so that I can keep track of my exercise habits. |  | 9 | F : T | 2 |  | Vincent King
As someone who walks a lot, I want a built-in step counter so I can track how far I walk each day. |  | 9 | F : T | 2 |  | Raven Goodell
Chris Vogel
Travis Tovey
Garrett Caruso