## Sheet1
ID | User Story | Sprint # | Priority | Status | Points
A1 | As a customer, I want to be able to record my age, weight, height, and gender to see a suggestion for daily caloric intake. | 3 | IP | IP | 2
A2 | As someone trying to get in shape, I want to be able to calculate what macronutrients I need to consume to reach my fitness goals. | 3 | H | W | 3
A3 | As someone trying to gain muscle, I want to receive suggestions on macronutrient intake based on my current intake to adjust my intake accordingly. | 3 | H | W | 3
A4 | As someone trying to gain weight, I want to be able to set a weight goal to receive a suggested daily caloric intake. | 3 | IP | IP | 1
A5 | As someone who is happy with their current weight, I want a built-in calorie calculator so I know how many calories I should consume to maintain my current weight. | 3 | IP | IP | 2
A6 | As someone trying to lose weight, I want to set custom weight loss goals so that the app will be more personalized to my needs. | 3 | H | W | 2
A7 | As someone trying to lose weight, I want to be able to track my progress towards my weight loss goal so that I can see how I am progressing. | 3 | H | W | 2
A8 | As a visual learner, I want a feature that will show me how many calories I've consumed each day in the form of a graph so that I can visually track my progress. | 4 | H | W | 3
A9 | As someone trying to eat healthier, I want to be able to record my sugar and sodium intake to track how close I am to my maximum recommended daily intake. | 4 | H | W | 1
A10 | As an app user, I want to be able to scan the barcode of packaged foods so that I can track my daily calorie intake more conveniently and accurately. | 5 | H | W | 2
A11 | As a user, I want to have calorie and macronutrient estimates for foods that do not have a nutrition label (e.g. fruits and vegetables) to help keep track of my daily intake. | 5 | H | W | 2
A12 | As an app user, I want to be able to input calories by searching for food so that I can log foods that do not have a barcode. | 6 | H | W | 2
B1 | As someone with visual problems, I want to be able to adjust font size to make the app more accessible. | 6 | M | IP | 1
B2 | As a colorblind person, I want the interface of the app to be colorblind friendly to make the app more accessible. | 6 | M | IP | 1
B3 | As a customer, I want to be able to set custom notifications and reminders so that I don't forget to log my data. | 7 | M | W | 2
B4 | As an app user, I want to be able to select my preferred way of measuring food so that the daily log of calories I've consumed will be more accurate. | 7 | M | W | 1
B5 | As someone who weighs food with a food scale, I want to input my foods in grams or ounces instead of suggested serving sizes. | 7 | M | W | 1
B6 | As someone just starting their weight loss journey, I want an optional tutorial to show me how the app works so that I do not feel intimidated. | 8 | M | W | 2
B7 | As an app user, I want a simple user interface to allow for easy navigation. | 5 | M | IP | 1
B8 | As an app user, I want the app's notifications to be positive and encouraging so that I will be more motivated to use the app to track my calorie intake. | 7 | M | W | 1
C1 | As someone who struggles with an eating disorder, I do not want to be encouraged to lose weight. | 3 | L | W | 1
C2 | As an app user, I want the app to have a dark mode so that it will not strain my eyes as much. | 8 | L | W | 1
C3 | As an app user, I want a feature that will allow me to track how much water I drink in a day so that I can make sure I am getting a proper amount of hydration. | 8 | L | W | 2
C4 | As an app user, I want to be able to change the color palette of the app's interface so that it will be more personalize and nicer to look at. | 8 | L | IP | 2
C5 | As an avid gym-goer, I want a feature that will allow me to log my workouts so that I can keep track of my exercise habits. | 9 | L | W | 3
C6 | As someone who walks a lot, I want a built-in step counter so I can track how far I walk each day. | 9 | L | W | 4